## Sheet1
#VALUE!
Data Contributors as of 6.9.25 to the Longitudinal Record
Name | Message Type | Prod Go Live | Backload Progess | Available Data: Our team is actively working to complete the loading of historical data into the FHIR repository, and we continue to add live data feeds daily as well. Below is the data that will be available once the work effort is fully complete, and column D of this document will provide progress updates on this data as it is available. - CCD data from October 2021 through present - Lab data for 6 months - Radiology results from production go-live date - Transcribed results from production go-live date - EKG results from production go-live date - Pathology results from production go-live date - ADTs from production go-live date
Allegan General Hospital | adt | 2025-04-28 | Production Go Live Date Forward
Allegan General Hospital | lab-oru | 2025-05-05 | Completed
Allegan General Hospital | rad-oru | 2025-05-05 | Production Go Live Date Forward
Aprima | ccda-ambulatory | 2025-05-21
Ascension Borgess Hospital | ccda-ambulatory | 2025-05-21
Ascension Borgess Hospital | ccda-medrec | 2025-05-21
Ascension Genesys Hospital | ccda-medrec | 2025-05-21
Ascension Genesys Hospital | lab-oru | 2025-05-06
Ascension Genesys Hospital | adt | 2025-05-22 | Production Go Live Date Forward
Ascension Genesys Hospital | ccda-ambulatory | 2025-05-21
Ascension Providence Rochester Hospital | ccda-ambulatory | 2025-05-21
Ascension Providence Rochester Hospital | ccda-medrec | 2025-05-21
Ascension St John Health System | ccda-ambulatory | 2025-05-22
Ascension St John Health System | ccda-medrec | 2025-05-22
Ascension St Joseph Hospital | ccda-medrec | 2025-05-22
Ascension St Marys Hospital | ccda-ambulatory | 2025-05-22
Ascension St Marys Hospital | ccda-medrec | 2025-05-22
Baldwin Family Healthcare | adt | 2025-04-28 | Production Go Live Date Forward
Baraga Community Memorial Hospital | ccda-medrec | 2025-05-30
Borgess | lab-oru | 2025-05-06
BORGESS | rad-oru | 2025-05-07 | Production Go Live Date Forward
Borgess Ambulatory | adt | 2025-04-29 | Production Go Live Date Forward
Borgess Inpatient | adt | 2025-04-29 | Production Go Live Date Forward
Cancer and Hematology Centers of Western Michigan | adt | 2025-04-29 | Production Go Live Date Forward
Cancer and Hematology Centers of Western Michigan | lab-oru | 2025-05-22
Capital Urological Associates | adt | 2025-04-29 | Production Go Live Date Forward
Careline Holdco | adt | 2025-04-30 | Production Go Live Date Forward
Caro Community Hospital | adt | 2025-04-30 | Production Go Live Date Forward
Caro Community Hospital | lab-oru | 2025-05-06 | Completed
Charlevoix Hospital | adt | 2025-05-01 | Production Go Live Date Forward
CHARLEVOIX HOSPITAL | rad-oru | 2025-05-19 | Production Go Live Date Forward
Cherry Health | adt | 2025-05-01 | Production Go Live Date Forward
Corewell Health | adt | 2025-05-20 | Production Go Live Date Forward
Corewell Health | ccda-ambulatory | 2025-05-30
Corewell Health | ccda-medrec | 2025-05-30
Corewell Health | lab-oru | 2025-05-20 | In Progress
Corewell Health | rad-oru | 2025-05-20 | Production Go Live Date Forward
Corewell Health | trans-mdm | 2025-05-20 | Production Go Live Date Forward
Corewell Health | trans-oru | 2025-05-20 | Production Go Live Date Forward
Covenant Hospital | adt | 2025-05-01 | Production Go Live Date Forward
Covenant Hospital | lab-oru | 2025-05-06
COVENANT HOSPITAL | rad-oru | 2025-05-22 | Production Go Live Date Forward
Eaton Rapids Medical Center | adt | 2025-05-01 | Production Go Live Date Forward
Eaton Rapids Medical Center | lab-oru | 2025-05-20 | Completed
EATON RAPIDS MEDICAL CENTER | trans-oru | 2025-05-08 | Production Go Live Date Forward
EATON RAPIDS MEDICAL CENTER | rad-oru | 2025-05-07 | Production Go Live Date Forward
GENESYS HOSPITAL | rad-oru | 2025-05-22 | Production Go Live Date Forward
Genesys Hospital (Ambulatory) | adt | 2025-05-01 | Production Go Live Date Forward
Gratiot Isabella Nephrology | adt | 2025-05-01 | Production Go Live Date Forward
Greenway | adt | 2025-05-01 | Production Go Live Date Forward
Harbor Beach | adt | 2025-05-01 | Production Go Live Date Forward
Henry Ford Health System | rad-oru | 2025-05-09 | Production Go Live Date Forward
Henry Ford Health System (GE Muse) | ekg-oru | 2025-05-08 | Production Go Live Date Forward
Hillsdale Hospital | adt | 2025-05-01 | Production Go Live Date Forward
Hillsdale Hospital | lab-oru | 2025-05-06
Hillsdale Hospital | path-oru | 2025-05-08 | Production Go Live Date Forward
HILLSDALE HOSPITAL | rad-oru | 2025-05-08 | Production Go Live Date Forward
HILLSDALE HOSPITAL | trans-oru | 2025-05-08 | Production Go Live Date Forward
Holland Hospital | adt | 2025-05-16 | Production Go Live Date Forward
Holland Hospital | ccda-ambulatory | 2025-05-30
Holland Hospital | ccda-medrec | 2025-05-30
Holland Hospital | lab-oru | 2025-05-21
Holland Hospital | path-oru | 2025-05-16 | Production Go Live Date Forward
Holland Hospital | rad-oru | 2025-05-16 | Production Go Live Date Forward
Holland Hospital | trans-oru | 2025-05-16 | Production Go Live Date Forward
Holland Hospital Physician Offices | adt | 2025-05-02 | Production Go Live Date Forward
Hurley | lab-oru | 2025-05-12
Hurley | adt | 2025-05-01 | Production Go Live Date Forward
HURLEY HOSPITAL | rad-oru | 2025-05-08 | Production Go Live Date Forward
Hurley Hospital | trans-mdm | 2025-05-12 | Production Go Live Date Forward
Infinity Primary Care | adt | 2025-05-02 | Production Go Live Date Forward
Ingenium DMC | lab-oru | 2025-05-22
Ingham County Health Dept | adt | 2025-05-02 | Production Go Live Date Forward
INGHAM COUNTY HEALTHDEPT | trans-oru | 2025-05-20 | Production Go Live Date Forward
JCMR | lab-oru | 2025-05-09
JCMR HFHS | adt | 2025-04-24 | Production Go Live Date Forward
Lake Huron | ekg-oru | 2025-05-12 | Production Go Live Date Forward
Lake Huron | lab-oru | 2025-05-06
Lake Huron | rad-oru | 2025-05-15 | Production Go Live Date Forward
Lake Huron | trans-mdm | 2025-05-12 | Production Go Live Date Forward
Lossio Pediatrics | adt | 2025-05-02 | Production Go Live Date Forward
Mckenzie Health System | adt | 2025-05-02 | Production Go Live Date Forward
McLaren | adt | 2025-05-02 | Production Go Live Date Forward
MCLAREN HOSPITAL (CERNER) | lab-oru | 2025-05-07
MCLAREN HOSPITAL (CERNER) | trans-oru | 2025-05-20 | Production Go Live Date Forward
MCLAREN HOSPITAL (CERNER) - | rad-oru | 2025-05-15 | Production Go Live Date Forward
MCLAREN KARMANOS HOSPITAL | lab-oru | 2025-05-22 | Completed
MCLAREN PORT HURON HOSPITAL | lab-oru | 2025-05-07 | Completed
MCLAREN PORT HURON HOSPITAL | trans-oru | 2025-05-20 | Production Go Live Date Forward
MCLAREN PORT HURON HOSPITAL - | rad-oru | 2025-05-15 | Production Go Live Date Forward
Michigan Medicine | ccda-medrec | 2025-06-03
Michigan Medicine | ccda-ambulatory | 2025-06-03
Michigan Medicine | rad-oru | 2025-06-02 | Production Go Live Date Forward
Michigan Medicine | trans-mdm | 2025-06-02 | Production Go Live Date Forward
Michigan Medicine | trans-mdm | 2025-06-02 | Production Go Live Date Forward
Michigan Medicine | trans-mdm | 2025-06-02 | Production Go Live Date Forward
Michigan Medicine | trans-oru | 2025-06-03 | Production Go Live Date Forward
Michigan Medicine | adt | 2025-06-02 | Production Go Live Date Forward
Michigan Medicine | lab-oru | 2025-06-02
Michigan Medicine - PEDs Cardio | trans-oru | 2025-06-02 | Production Go Live Date Forward
Midland Family Physicians | adt | 2025-05-02 | Production Go Live Date Forward
MIDMICHIGAN HEALTH HOSPITAL | lab-oru | 2025-05-07
MIDMICHIGAN HEALTH HOSPITAL | rad-oru | 2025-05-15 | Production Go Live Date Forward
MIDMICHIGAN HEALTH HOSPITAL | trans-oru | 2025-05-20 | Production Go Live Date Forward
MidMichigan Health Hospital (MyMichigan Health) | adt | 2025-05-02 | Production Go Live Date Forward
MIDMICHIGAN RADIOLOGY ASSOC | rad-oru | 2025-05-15 | Production Go Live Date Forward
MidMichigan Radiology Associates | adt | 2025-05-02 | Production Go Live Date Forward
Munson Health Care | ccda-ambulatory | 2025-05-30
Munson Health Care | ccda-medrec | 2025-05-30
Munson Hospital | adt | 2025-05-16 | Production Go Live Date Forward
Munson Hospital | lab-oru | 2025-05-19
Munson Hospital | rad-oru | 2025-05-19 | Production Go Live Date Forward
Munson Hospital | trans-oru | 2025-05-19 | Production Go Live Date Forward
NextCare LAB-ORU | lab-oru | 2025-05-07 | Completed
Oaklawn Hospital | adt | 2025-05-02 | Production Go Live Date Forward
OAKLAWN HOSPITAL | lab-oru | 2025-05-07
OAKLAWN HOSPITAL | trans-oru | 2025-05-20 | Production Go Live Date Forward
OAKLAWN HOSPITAL | rad-oru | 2025-05-15 | Production Go Live Date Forward
Owosso Memorial Hospital | adt | 2025-05-05 | Production Go Live Date Forward
Parkview for RxStrategies | adt | 2025-05-05 | Production Go Live Date Forward
PCE NEXUS PAYER GATEWAY | adt | 2025-05-19 | Production Go Live Date Forward
Promedica | adt | 2025-04-24 | Production Go Live Date Forward
Promedica Monroe Hospital | lab-oru | 2025-05-12
Sparrow Health Hospital | adt | 2025-05-20 | Production Go Live Date Forward
Sparrow Health Hospital | rad-oru | 2025-05-20 | Production Go Live Date Forward
Sparrow Health Hospital | trans-mdm | 2025-05-20 | Production Go Live Date Forward
ST JOHN | lab-oru | 2025-05-07
ST JOHN | trans-oru | 2025-05-20 | Production Go Live Date Forward
ST JOHN | adt | 2025-05-05 | Production Go Live Date Forward
ST JOHN | rad-oru | 2025-05-15 | Production Go Live Date Forward
Straith Hospital for Special Surgery | adt | 2025-05-05 | Production Go Live Date Forward
THREE RIVERS HOSPITAL | lab-oru | 2025-05-07 | In Progress
Trinity Health | adt | 2025-06-03 | Production Go Live Date Forward
Trinity Health | ccda-ambulatory
Trinity Health | ccda-medrec
Trinity Health | ekg-oru
Trinity Health | lab-oru
Trinity Health | path-oru
Trinity Health | rad-oru
Trinity Health | trans-mdm
Trinity Health - Grand Haven | ccda-medrec
Trinity Health - Grand Haven | lab-oru
Trinity Health - Grand Haven | rad-oru
Trinity Health - Grand Haven | trans-oru
Trinity Health - Grand Haven | adt | 2025-06-09 | Production Go Live Date Forward
University of Michigan Health - Sparrow | ccda-ambulatory | 2025-05-30
University of Michigan Health - Sparrow | ccda-medrec | 2025-05-30
University of Michigan Health - Sparrow | lab-oru | 2025-05-30
University of Michigan Health - West | lab-oru | 2025-06-03 | Completed
University of Michigan Health - West | adt | 2025-06-03 | Production Go Live Date Forward
UPHIE Aspirus | lab-oru | 2025-05-21
UPHIE Aspirus | adt | 2025-05-21 | Production Go Live Date Forward
UPHIE Aspirus | ccda-ambulatory | 2025-05-30
UPHIE Aspirus | ccda-medrec | 2025-05-30
UPHIE Baraga County Memorial | lab-oru | 2025-05-07 | Completed
UPHIE Baraga County Memorial | adt | 2025-05-06 | Production Go Live Date Forward
UPHIE Baraga County Memorial | rad-oru | 2025-05-16 | Production Go Live Date Forward
UPHIE Bell | lab-oru | 2025-05-07 | Completed
UPHIE Bell | adt | 2025-05-06 | Production Go Live Date Forward
UPHIE Bell | rad-oru | 2025-05-16 | Production Go Live Date Forward
UPHIE Bronson | adt | 2025-05-08 | Production Go Live Date Forward
UPHIE Bronson | lab-oru | 2025-05-12
UPHIE Dickinson | lab-oru | 2025-05-12
UPHIE Dickinson | adt | 2025-05-08 | Production Go Live Date Forward
UPHIE Dickinson | rad-oru | 2025-05-19 | Production Go Live Date Forward
UPHIE Helen Newberry Joy | adt | 2025-05-08 | Production Go Live Date Forward
UPHIE Mackinac | lab-oru | 2025-05-12 | Completed
UPHIE Mackinac | adt | 2025-05-09 | Production Go Live Date Forward
UPHIE Marquette | lab-oru | 2025-05-12
UPHIE Marquette | adt | 2025-05-09 | Production Go Live Date Forward
UPHIE Munising | lab-oru | 2025-05-12 | Completed
UPHIE Munising | adt | 2025-05-09 | Production Go Live Date Forward
UPHIE Munising | rad-oru | 2025-05-19 | Production Go Live Date Forward
UPHIE OSF | lab-oru | 2025-05-12
UPHIE OSF | adt | 2025-05-09 | Production Go Live Date Forward
UPHIE OSF | rad-oru | 2025-05-19 | Production Go Live Date Forward
UPHIE Portage | lab-oru | 2025-05-12 | Completed
UPHIE Portage | adt | 2025-05-09 | Production Go Live Date Forward
UPHIE Portage | rad-oru | 2025-05-19 | Production Go Live Date Forward
UPHIE Schoolcraft | lab-oru | 2025-05-12 | In Progress
UPHIE Schoolcraft | adt | 2025-05-09 | Production Go Live Date Forward
UPHIE Schoolcraft | rad-oru | 2025-05-19 | Production Go Live Date Forward
UPHIE War Memorial | lab-oru | 2025-05-12